Minutes of the Meeting

Monitoring Meeting in Slovakia

Work Package No. 3 – Inspire, Develop and Achieve: FLIGHT Resource Center Projects

1. Meeting Details

Date: 16–17 April 2026
Venue: Stredná priemyselná škola stavebná – Építőipari Szakközépiskola, Konkolyho 8, Hurbanovo, Slovakia
Host organisation: SPŠS – ÉKI Konkolyho 8 Hurbanovo, Slovakia

The Monitoring Meeting in Slovakia was organised under Work Package No. 3 – Inspire, Develop and Achieve: FLIGHT Resource Center Projects. The meeting took place at Stredná priemyselná škola stavebná – Építőipari Szakközépiskola, Konkolyho 8, Hurbanovo, on 16–17 April 2026.

2. Participants

The meeting was attended by representatives of the following partner organisations:

- Darıca İlçe MEM, Türkiye

- Gebze Technical University, Türkiye

- GASKİ Genel Müdürlüğü, Türkiye

- Training 2000, Italy

- Sucessos Criativos, Portugal

- DSU-RCSOO Kiro Burnaz, North Macedonia

- SPŠS – ÉKI Konkolyho 8 Hurbanovo, Slovakia

The attendance list included the following participants: Mehmet Emin Uğur, Harun Yenişan, Ejder Güven, Selcuk Toprak, Ali Levent Yagci, Banu Cetin, Cigdem Balcik, Oguz Dal, Tuğba Kömürcü, Sedat Gülmüş, Kylene De Angelis, Sara Caboni, Fátima Pais, Luís Soares, Silvana Josifovska Tasikj, Frosina Stojanovska, and Katarína Kučerová.

3. Agenda and Main Discussion Points

3.1 Requirements and Specifications for Project Videos

The project partners discussed the requirements and technical specifications for the videos to be prepared and uploaded as part of the project activities.

It was agreed that each partner organisation is required to prepare at least five videos. The maximum length of each video is 90 seconds. The opening and closing slides for the videos were provided by Training 2000, the partner organisation from Italy.

Each video must clearly present its purpose and provide understandable information for the target audience. Where possible, videos should also include subtitles and/or a voiceover to improve accessibility and clarity.

The videos will be uploaded to YouTube. The YouTube channel and each individual video should include a short explanation describing the content and purpose of the video.

A shared Excel sheet will be created and managed by the Portuguese partner, Sucessos Criativos. All participating organisations will enter the title of each video and a short description into this Excel sheet.

Deadline for uploading the videos: end of October 2026.

3.2 Online Questionnaires for Local Replication Workshops

The partners discussed the preparation of online questionnaires for the local replication workshops.

The questionnaires will be prepared by Training 2000. Two versions of the questionnaire will be available:

- one version for students,

- one version for teachers.

The questionnaires may also be used with students in connection with the replication workshops. Their purpose is to collect feedback and support the evaluation of the implemented activities.

Deadline for completing the questionnaires: after the local replication workshops.

3.3 Guidebook / Handbook Translation

The partners discussed the translation of the project Guidebook / Handbook.

All participating organisations are required to translate the Guidebook / Handbook into their national languages. Partners must follow the common template and respect the agreed formatting rules, including the specified font, font size, structure, and general visual standards.

The purpose is to ensure that all translated materials are consistent and follow the same technical and formal requirements.

Deadline for Guidebook / Handbook translation: 15 May 2026.

3.4 Evaluation of Work Package No. 2

The partners noted that the evaluation of Work Package No. 2 will be carried out at the end of April 2026.

This activity will be coordinated under the responsibility of Training 2000.

3.5 Work Package No. 3 – Resource Center

The partners discussed the current state of the project Resource Center.

It was reported that the Resource Center has already been created and that 17 projects have already been published. These projects have also been disseminated through social media.

The Portuguese partner representative, Luís Soares, is responsible for completing the relevant sections of the Excel sheet connected to the Resource Center materials.

In the Excel sheet, all partners should indicate:

- whether the required changes have been made,

- whether the materials have been reviewed,

- the date of review,

- and the date of publication.

The partners also discussed the folder structure in the shared drive. The folder marked “Old” contains materials that need to be reviewed, changed, or modified. The folder marked “New” must contain updated materials and translations in all partner languages.

All materials that will be published in the Resource Center must also be available in the national languages of the partner organisations.

Deadline for completing translations for the Resource Center: 20 May 2026.

A follow-up meeting will be scheduled by DİMM / Darıca İlçe MEM by 20 May 2026.

3.6 Selection of Best Practices

From all created projects, partners will select two projects to be presented as best practices.

The selected best practices will be further developed and described using a common template.

3.7 Overall Final Project Meeting in Gaziantep, Türkiye

The partners discussed the overall final project meeting.

The meeting will take place in Gaziantep, Türkiye, on:

21–22 September 2026

Each partner organisation is expected to send two representatives to the final project meeting.

3.8 Best Practice Report Template

The partners discussed the format, structure, and content of the Best Practice Report.

The template will be provided by the Portuguese partner, Sucessos Criativos. It will have a clear structure and is expected to be approximately 10 pages in total, with around 5 pages per best practice.

The partners agreed that the Best Practice Report should not simply repeat the content of the lesson plans. Instead, it should provide a structured presentation of the selected best practices, including methodology, impact on students, recommendations, and relevant supporting materials. Pictures should be included where appropriate.

The Best Practice Report template will be saved in the shared drive.

Deadline for publishing the Best Practice Report template: end of April 2026.
Deadline for preparing the Best Practice Report: by September 2026.
Deadline for translating the Best Practice Report: end of October 2026.

4. Distribution of Responsibilities for the Best Practice Report

The partners agreed on the following role distribution:

| Section / Point | Responsible Partner |
| --- | --- |
| Point 1 – Introduction / general description, approx. 3 pages | Sucessos Criativos, Portugal |
| Point 2 – Methodology, approx. 3–5 pages | Gebze Technical University, Türkiye |
| Point 3 | DİMM / Darıca İlçe MEM, Türkiye |
| Point 4 | All partners |
| Point 5 – Recommendations | Training 2000, Italy and DSU-RCSOO Kiro Burnaz, North Macedonia |
| Point 6 – General review | Slovak partner, SPŠS – ÉKI Hurbanovo |

The report should also include information on the impact on students.

5. Action Plan and Deadlines

| No. | Task | Responsible Partner(s) | Deadline |
| --- | --- | --- | --- |
| 1 | Prepare at least five project videos per partner | All partners | End of October 2026 |
| 2 | Use the provided opening and closing slides in all videos | All partners | Ongoing |
| 3 | Upload videos to YouTube with short descriptions | All partners | End of October 2026 |
| 4 | Create and manage the Excel sheet for video titles and descriptions | Sucessos Criativos, Portugal | To be prepared |
| 5 | Complete the Excel sheet with video titles and descriptions | All partners | End of October 2026 |
| 6 | Prepare online questionnaires for students and teachers | Training 2000, Italy | Before / during local replication workshop phase |
| 7 | Complete questionnaires | All relevant partners / participants | After local replication workshops |
| 8 | Translate the Guidebook / Handbook into national languages | All partners | 15 May 2026 |
| 9 | Carry out evaluation of Work Package No. 2 | Training 2000, Italy | End of April 2026 |
| 10 | Review Resource Center materials and complete required information in Excel sheet | All partners, coordinated through the shared Excel sheet |  |
| 11 | Complete translations of Resource Center materials | All partners | 20 May 2026 |
| 12 | Schedule follow-up meeting on Resource Center materials | DİMM / Darıca İlçe MEM, Türkiye | By 20 May 2026 |
| 13 | Select two best-practice projects | All partners | By September 2026 |
| 14 | Provide Best Practice Report template | Sucessos Criativos, Portugal | End of April 2026 |
| 15 | Prepare Best Practice Report according to role distribution | Responsible partners according to assigned sections | By September 2026 |
| 16 | Translate Best Practice Report | All partners | End of October 2026 |
| 17 | Conduct general review of the Best Practice Report | Slovak partner, SPŠS – ÉKI Hurbanovo | To be confirmed |
| 18 | Attend the overall final project meeting in Gaziantep | Two representatives per partner organisation | 21–22 September 2026 |

6. Conclusions and Next Steps

The partners agreed on the requirements for the project videos, the preparation and use of online questionnaires, the translation of the Guidebook / Handbook, and the further development of the Resource Center. They also discussed the selection and presentation of two best-practice projects and agreed on the structure and responsibilities for the Best Practice Report.

The next steps will focus on completing translations, reviewing Resource Center materials, preparing and uploading videos, finalising the Best Practice Report template, and preparing for the overall final project meeting in Gaziantep, Türkiye, on 21–22 September 2026.

Prepared by:
SPŠS – ÉKI Konkolyho 8 Hurbanovo, Slovakia
Date of preparation: 29 April 2026